## Summary
POWER PARK STUDENT HOUSING — PHASE 3
Inspection Points to Visit — Project Summary
190 four-bed units · 3 blocks · snapshot 09 Jun 2026 (DB SNAP 2026-06-09 09:59 UTC)
TOTAL SCOPE |  | PASSED (OK) |  | % PASSED |  | POINTS TO VISIT | TRULY CERTIFIED
95716 |  | 83046 |  | 86.76% |  | 12739 | 2
inspection points |  | points marked MS/OK |  | of total scope |  | on-site actions remaining | units, every axis clean
WHAT REMAINS (the Points to Visit)
Pending — not yet inspected |  |  | 5881
NTS — failed, awaiting re-mark |  |  | 2140
Not installed |  |  | 12
Skipped — previously excluded, now in scope |  |  | 4637
Items to Mark (subtotal) |  |  | 12670
Latent defects to rectify |  |  | 69
POINTS TO VISIT (Items to Mark + Latents) |  |  | 12739
Reconciliation check: Passed + Items to Mark = Total Scope → |  |  | 95716
BLOCK ROLLUP
Block |  | Units | Total Points | Passed | % Passed | Points to Visit
Block 1 |  | 8 | 4016 | 3457 | 86.08% | 560
Block 2 |  | 8 | 4016 | 3217 | 80.1% | 799
Block 3 |  | 37 | 18640 | 16350 | 87.71% | 2296
Block 4 |  | 42 | 21168 | 18271 | 86.31% | 2930
Block 5 |  | 42 | 21168 | 18964 | 89.59% | 2204
Block 6 |  | 36 | 18144 | 15832 | 87.26% | 2338
Block 7 |  | 17 | 8564 | 6955 | 81.21% | 1612
TOTAL |  | 190 | 95716 | 83046 | 86.76% | 12739
BLOCK x FLOOR GRID
Block | Floor | Units | Total Points | Passed | % Passed | Points to Visit
Block 1 | 1 | 2 | 1004 | 954 | 95.02% | 50
Block 1 | 2 | 6 | 3012 | 2503 | 83.1% | 510
Block 2 | 1 | 4 | 2008 | 1524 | 75.9% | 484
Block 2 | 2 | 4 | 2008 | 1693 | 84.31% | 315
Block 3 | 0 | 11 | 5588 | 4852 | 86.83% | 742
Block 3 | 1 | 13 | 6526 | 6014 | 92.15% | 512
Block 3 | 2 | 13 | 6526 | 5484 | 84.03% | 1042
Block 4 | 0 | 14 | 7112 | 5996 | 84.31% | 1131
Block 4 | 1 | 14 | 7028 | 5442 | 77.43% | 1604
Block 4 | 2 | 14 | 7028 | 6833 | 97.23% | 195
Block 5 | 0 | 14 | 7112 | 6297 | 88.54% | 815
Block 5 | 1 | 14 | 7028 | 6438 | 91.61% | 590
Block 5 | 2 | 14 | 7028 | 6229 | 88.63% | 799
Block 6 | 0 | 12 | 6096 | 5485 | 89.98% | 611
Block 6 | 1 | 12 | 6024 | 5523 | 91.68% | 501
Block 6 | 2 | 12 | 6024 | 4824 | 80.08% | 1226
Block 7 | 0 | 5 | 2540 | 2281 | 89.8% | 259
Block 7 | 1 | 6 | 3012 | 2200 | 73.04% | 812
Block 7 | 2 | 6 | 3012 | 2474 | 82.14% | 541
TOTAL |  | 190 | 95716 | 83046 | 86.76% | 12739

## 190-Unit Detail
INSPECTION POINTS TO VISIT — 190 UNITS (per-unit detail)
Total Points = 508 (ground) / 502 (above ground = 508 active points less 6 ground-only burglar-bar items, structurally absent upstairs). Items to Mark = Pending + NTS + Not Inst + Skipped. Already OK + Items to Mark = Total Points (row closes). POINTS TO VISIT = Items to Mark + Latents. Open Defects shown for context only — NOT added to PTV (they sit on the NTS items already counted). Source: /var/data/inspections.db, SNAP 2026-06-09 09:59 UTC.
Unit | Block | Floor | Cycle | Status | Total Points | Already OK | Pending | NTS | Not Inst | Skipped | Items to Mark | Latents | POINTS TO VISIT | Open Defects (context — not in PTV)
101 | Block 1 | 1 | C2 | reviewed | 502 | 479 | 15 | 8 | 0 | 0 | 23 | 0 | 23 | 22
102 | Block 1 | 1 | C2 | reviewed | 502 | 475 | 23 | 4 | 0 | 0 | 27 | 0 | 27 | 28
201 | Block 1 | 2 | C1 | pending followup | 502 | 308 | 0 | 134 | 6 | 54 | 194 | 0 | 194 | 185
202 | Block 1 | 2 | C1 | pending followup | 502 | 362 | 0 | 86 | 0 | 54 | 140 | 0 | 140 | 112
248 | Block 1 | 2 | C2 | pending followup | 502 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | Block 1 | 2 | C2 | pending followup | 502 | 356 | 92 | 0 | 0 | 54 | 146 | 1 | 147 | 1
250 | Block 1 | 2 | C3 | submitted | 502 | 478 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 0
251 | Block 1 | 2 | C2 | pending followup | 502 | 497 | 0 | 5 | 0 | 0 | 5 | 0 | 5 | 1
144 | Block 2 | 1 | C2 | pending followup | 502 | 367 | 127 | 8 | 0 | 0 | 135 | 0 | 135 | 43
145 | Block 2 | 1 | C2 | pending followup | 502 | 377 | 118 | 7 | 0 | 0 | 125 | 0 | 125 | 15
146 | Block 2 | 1 | C2 | pending followup | 502 | 401 | 99 | 2 | 0 | 0 | 101 | 0 | 101 | 1
147 | Block 2 | 1 | C2 | pending followup | 502 | 379 | 116 | 7 | 0 | 0 | 123 | 0 | 123 | 7
244 | Block 2 | 2 | C2 | pending followup | 502 | 402 | 98 | 2 | 0 | 0 | 100 | 0 | 100 | 2
245 | Block 2 | 2 | C2 | pending followup | 502 | 425 | 75 | 2 | 0 | 0 | 77 | 0 | 77 | 2
246 | Block 2 | 2 | C2 | pending followup | 502 | 373 | 127 | 2 | 0 | 0 | 129 | 0 | 129 | 1
247 | Block 2 | 2 | C2 | pending followup | 502 | 493 | 0 | 9 | 0 | 0 | 9 | 0 | 9 | 4
002 | Block 3 | 0 | C2 | pending followup | 508 | 464 | 44 | 0 | 0 | 0 | 44 | 0 | 44 | 2
003 | Block 3 | 0 | C2 | pending followup | 508 | 402 | 106 | 0 | 0 | 0 | 106 | 0 | 106 | 2
004 | Block 3 | 0 | C2 | pending followup | 508 | 467 | 38 | 3 | 0 | 0 | 41 | 0 | 41 | 1
005 | Block 3 | 0 | C2 | pending followup | 508 | 404 | 100 | 4 | 0 | 0 | 104 | 0 | 104 | 4
006 | Block 3 | 0 | C2 | pending followup | 508 | 382 | 123 | 3 | 0 | 0 | 126 | 0 | 126 | 5
007 | Block 3 | 0 | C2 | pending followup | 508 | 468 | 38 | 2 | 0 | 0 | 40 | 0 | 40 | 3
008 | Block 3 | 0 | C2 | pending followup | 508 | 398 | 98 | 12 | 0 | 0 | 110 | 4 | 114 | 31
009 | Block 3 | 0 | C2 | pending followup | 508 | 469 | 26 | 13 | 0 | 0 | 39 | 0 | 39 | 16
010 | Block 3 | 0 | C2 | pending followup | 508 | 455 | 42 | 11 | 0 | 0 | 53 | 0 | 53 | 20
011 | Block 3 | 0 | C2 | pending followup | 508 | 474 | 10 | 24 | 0 | 0 | 34 | 0 | 34 | 5
012 | Block 3 | 0 | C2 | pending followup | 508 | 469 | 11 | 28 | 0 | 0 | 39 | 2 | 41 | 7
103 | Block 3 | 1 | C2 | reviewed | 502 | 481 | 16 | 5 | 0 | 0 | 21 | 0 | 21 | 21
104 | Block 3 | 1 | C2 | reviewed | 502 | 477 | 15 | 10 | 0 | 0 | 25 | 0 | 25 | 26
105 | Block 3 | 1 | C2 | reviewed | 502 | 475 | 13 | 14 | 0 | 0 | 27 | 0 | 27 | 25
106 | Block 3 | 1 | C2 | reviewed | 502 | 482 | 11 | 9 | 0 | 0 | 20 | 0 | 20 | 20
107 | Block 3 | 1 | C2 | reviewed | 502 | 473 | 17 | 12 | 0 | 0 | 29 | 0 | 29 | 27
108 | Block 3 | 1 | C2 | reviewed | 502 | 486 | 8 | 8 | 0 | 0 | 16 | 0 | 16 | 13
109 | Block 3 | 1 | C2 | reviewed | 502 | 469 | 15 | 18 | 0 | 0 | 33 | 0 | 33 | 30
110 | Block 3 | 1 | C2 | reviewed | 502 | 474 | 20 | 8 | 0 | 0 | 28 | 0 | 28 | 27
111 | Block 3 | 1 | C2 | reviewed | 502 | 474 | 15 | 13 | 0 | 0 | 28 | 0 | 28 | 28
112 | Block 3 | 1 | C2 | pending followup | 502 | 383 | 112 | 7 | 0 | 0 | 119 | 0 | 119 | 25
113 | Block 3 | 1 | C2 | pending followup | 502 | 448 | 44 | 10 | 0 | 0 | 54 | 0 | 54 | 6
114 | Block 3 | 1 | C2 | pending followup | 502 | 449 | 48 | 5 | 0 | 0 | 53 | 0 | 53 | 5
115 | Block 3 | 1 | C2 | pending followup | 502 | 443 | 49 | 10 | 0 | 0 | 59 | 0 | 59 | 6
203 | Block 3 | 2 | C2 | reviewed | 502 | 474 | 19 | 9 | 0 | 0 | 28 | 0 | 28 | 27
204 | Block 3 | 2 | C2 | reviewed | 502 | 485 | 10 | 7 | 0 | 0 | 17 | 0 | 17 | 14
205 | Block 3 | 2 | C2 | reviewed | 502 | 483 | 13 | 6 | 0 | 0 | 19 | 0 | 19 | 16
206 | Block 3 | 2 | C2 | reviewed | 502 | 437 | 61 | 4 | 0 | 0 | 65 | 0 | 65 | 18
207 | Block 3 | 2 | C2 | reviewed | 502 | 447 | 35 | 20 | 0 | 0 | 55 | 0 | 55 | 49
208 | Block 3 | 2 | C1 | pending followup | 502 | 412 | 0 | 90 | 0 | 0 | 90 | 0 | 90 | 126
209 | Block 3 | 2 | C1 | pending followup | 502 | 401 | 0 | 101 | 0 | 0 | 101 | 0 | 101 | 137
210 | Block 3 | 2 | C1 | pending followup | 502 | 376 | 0 | 126 | 0 | 0 | 126 | 0 | 126 | 169
211 | Block 3 | 2 | C1 | pending followup | 502 | 402 | 0 | 94 | 6 | 0 | 100 | 0 | 100 | 122
212 | Block 3 | 2 | C1 | pending followup | 502 | 389 | 0 | 113 | 0 | 0 | 113 | 0 | 113 | 140
213 | Block 3 | 2 | C1 | pending followup | 502 | 400 | 0 | 102 | 0 | 0 | 102 | 0 | 102 | 126
214 | Block 3 | 2 | C1 | pending followup | 502 | 378 | 0 | 124 | 0 | 0 | 124 | 0 | 124 | 145
215 | Block 3 | 2 | C1 | pending followup | 502 | 400 | 0 | 102 | 0 | 0 | 102 | 0 | 102 | 136
013 | Block 4 | 0 | C2 | pending followup | 508 | 493 | 0 | 15 | 0 | 0 | 15 | 0 | 15 | 2
014 | Block 4 | 0 | C2 | pending followup | 508 | 505 | 0 | 3 | 0 | 0 | 3 | 0 | 3 | 0
015 | Block 4 | 0 | C2 | pending followup | 508 | 505 | 0 | 3 | 0 | 0 | 3 | 0 | 3 | 0
016 | Block 4 | 0 | C2 | pending followup | 508 | 493 | 0 | 15 | 0 | 0 | 15 | 0 | 15 | 0
017 | Block 4 | 0 | C2 | pending followup | 508 | 489 | 0 | 19 | 0 | 0 | 19 | 0 | 19 | 1
018 | Block 4 | 0 | C2 | pending followup | 508 | 407 | 47 | 0 | 0 | 54 | 101 | 1 | 102 | 5
019 | Block 4 | 0 | C2 | pending followup | 508 | 382 | 72 | 0 | 0 | 54 | 126 | 0 | 126 | 24
020 | Block 4 | 0 | C2 | pending followup | 508 | 355 | 99 | 0 | 0 | 54 | 153 | 5 | 158 | 10
021 | Block 4 | 0 | C2 | pending followup | 508 | 376 | 78 | 0 | 0 | 54 | 132 | 2 | 134 | 2
022 | Block 4 | 0 | C2 | pending followup | 508 | 365 | 89 | 0 | 0 | 54 | 143 | 3 | 146 | 7
023 | Block 4 | 0 | C3 | submitted | 508 | 489 | 0 | 19 | 0 | 0 | 19 | 1 | 20 | 0
024 | Block 4 | 0 | C2 | pending followup | 508 | 385 | 69 | 0 | 0 | 54 | 123 | 1 | 124 | 1
025 | Block 4 | 0 | C2 | pending followup | 508 | 370 | 84 | 0 | 0 | 54 | 138 | 2 | 140 | 3
026 | Block 4 | 0 | C2 | pending followup | 508 | 382 | 72 | 0 | 0 | 54 | 126 | 0 | 126 | 2
116 | Block 4 | 1 | C2 | pending followup | 502 | 363 | 85 | 0 | 0 | 54 | 139 | 4 | 143 | 4
117 | Block 4 | 1 | C2 | pending followup | 502 | 309 | 139 | 0 | 0 | 54 | 193 | 0 | 193 | 2
118 | Block 4 | 1 | C2 | pending followup | 502 | 323 | 125 | 0 | 0 | 54 | 179 | 4 | 183 | 11
119 | Block 4 | 1 | C2 | pending followup | 502 | 381 | 67 | 0 | 0 | 54 | 121 | 1 | 122 | 7
120 | Block 4 | 1 | C2 | pending followup | 502 | 341 | 107 | 0 | 0 | 54 | 161 | 0 | 161 | 5
121 | Block 4 | 1 | C2 | pending followup | 502 | 371 | 77 | 0 | 0 | 54 | 131 | 0 | 131 | 1
122 | Block 4 | 1 | C2 | pending followup | 502 | 392 | 56 | 0 | 0 | 54 | 110 | 3 | 113 | 3
123 | Block 4 | 1 | C2 | pending followup | 502 | 364 | 84 | 0 | 0 | 54 | 138 | 4 | 142 | 1
124 | Block 4 | 1 | C2 | pending followup | 502 | 375 | 73 | 0 | 0 | 54 | 127 | 1 | 128 | 1
125 | Block 4 | 1 | C2 | pending followup | 502 | 385 | 63 | 0 | 0 | 54 | 117 | 0 | 117 | 9
126 | Block 4 | 1 | C2 | pending followup | 502 | 370 | 78 | 0 | 0 | 54 | 132 | 1 | 133 | 12
127 | Block 4 | 1 | C2 | pending followup | 502 | 490 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | 3
128 | Block 4 | 1 | C2 | pending followup | 502 | 480 | 0 | 22 | 0 | 0 | 22 | 0 | 22 | 7
129 | Block 4 | 1 | C2 | pending followup | 502 | 498 | 3 | 1 | 0 | 0 | 4 | 0 | 4 | 4
216 | Block 4 | 2 | C2 | pending followup | 502 | 486 | 8 | 8 | 0 | 0 | 16 | 0 | 16 | 11
217 | Block 4 | 2 | C2 | pending followup | 502 | 491 | 6 | 5 | 0 | 0 | 11 | 0 | 11 | 8
218 | Block 4 | 2 | C2 | pending followup | 502 | 495 | 2 | 5 | 0 | 0 | 7 | 0 | 7 | 3
219 | Block 4 | 2 | C2 | pending followup | 502 | 489 | 2 | 11 | 0 | 0 | 13 | 0 | 13 | 7
220 | Block 4 | 2 | C2 | reviewed | 502 | 475 | 13 | 14 | 0 | 0 | 27 | 0 | 27 | 24
221 | Block 4 | 2 | C2 | reviewed | 502 | 436 | 41 | 25 | 0 | 0 | 66 | 0 | 66 | 65
222 | Block 4 | 2 | C2 | pending followup | 502 | 492 | 5 | 5 | 0 | 0 | 10 | 0 | 10 | 6
223 | Block 4 | 2 | C2 | pending followup | 502 | 496 | 1 | 5 | 0 | 0 | 6 | 0 | 6 | 2
224 | Block 4 | 2 | C2 | pending followup | 502 | 491 | 4 | 7 | 0 | 0 | 11 | 0 | 11 | 7
225 | Block 4 | 2 | C2 | pending followup | 502 | 497 | 1 | 4 | 0 | 0 | 5 | 0 | 5 | 1
226 | Block 4 | 2 | C2 | pending followup | 502 | 495 | 1 | 6 | 0 | 0 | 7 | 0 | 7 | 3
227 | Block 4 | 2 | C2 | pending followup | 502 | 498 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 0
228 | Block 4 | 2 | C2 | pending followup | 502 | 496 | 1 | 5 | 0 | 0 | 6 | 0 | 6 | 1
229 | Block 4 | 2 | C2 | pending followup | 502 | 496 | 0 | 6 | 0 | 0 | 6 | 0 | 6 | 2
027 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
028 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
029 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
030 | Block 5 | 0 | C3 | reviewed | 508 | 449 | 8 | 0 | 0 | 51 | 59 | 0 | 59 | 0
031 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
032 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
033 | Block 5 | 0 | C3 | reviewed | 508 | 449 | 12 | 0 | 0 | 47 | 59 | 0 | 59 | 1
034 | Block 5 | 0 | C3 | reviewed | 508 | 449 | 12 | 0 | 0 | 47 | 59 | 0 | 59 | 1
035 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
036 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
037 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
038 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
039 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
040 | Block 5 | 0 | C3 | reviewed | 508 | 450 | 11 | 0 | 0 | 47 | 58 | 0 | 58 | 0
130 | Block 5 | 1 | C3 | reviewed | 502 | 450 | 21 | 2 | 0 | 29 | 52 | 0 | 52 | 0
131 | Block 5 | 1 | C3 | reviewed | 502 | 456 | 15 | 2 | 0 | 29 | 46 | 0 | 46 | 0
132 | Block 5 | 1 | C3 | reviewed | 502 | 453 | 17 | 2 | 0 | 30 | 49 | 0 | 49 | 0
133 | Block 5 | 1 | C3 | reviewed | 502 | 454 | 17 | 2 | 0 | 29 | 48 | 0 | 48 | 0
134 | Block 5 | 1 | C3 | reviewed | 502 | 438 | 32 | 2 | 0 | 30 | 64 | 0 | 64 | 0
135 | Block 5 | 1 | C3 | reviewed | 502 | 462 | 8 | 2 | 0 | 30 | 40 | 0 | 40 | 0
136 | Block 5 | 1 | C3 | reviewed | 502 | 462 | 8 | 2 | 0 | 30 | 40 | 0 | 40 | 0
137 | Block 5 | 1 | C3 | reviewed | 502 | 462 | 8 | 2 | 0 | 30 | 40 | 0 | 40 | 0
138 | Block 5 | 1 | C3 | reviewed | 502 | 463 | 8 | 2 | 0 | 29 | 39 | 0 | 39 | 0
139 | Block 5 | 1 | C3 | reviewed | 502 | 462 | 8 | 2 | 0 | 30 | 40 | 0 | 40 | 0
140 | Block 5 | 1 | C3 | reviewed | 502 | 463 | 8 | 2 | 0 | 29 | 39 | 0 | 39 | 0
141 | Block 5 | 1 | C3 | reviewed | 502 | 471 | 11 | 2 | 0 | 18 | 31 | 0 | 31 | 0
142 | Block 5 | 1 | C3 | reviewed | 502 | 471 | 11 | 2 | 0 | 18 | 31 | 0 | 31 | 0
143 | Block 5 | 1 | C3 | reviewed | 502 | 471 | 11 | 2 | 0 | 18 | 31 | 0 | 31 | 0
230 | Block 5 | 2 | C3 | submitted | 502 | 448 | 8 | 12 | 0 | 34 | 54 | 0 | 54 | 0
231 | Block 5 | 2 | C3 | submitted | 502 | 447 | 8 | 27 | 0 | 20 | 55 | 0 | 55 | 0
232 | Block 5 | 2 | C3 | submitted | 502 | 457 | 8 | 17 | 0 | 20 | 45 | 0 | 45 | 2
233 | Block 5 | 2 | C3 | submitted | 502 | 450 | 8 | 25 | 0 | 19 | 52 | 0 | 52 | 0
234 | Block 5 | 2 | C3 | submitted | 502 | 456 | 8 | 18 | 0 | 20 | 46 | 0 | 46 | 1
235 | Block 5 | 2 | C3 | reviewed | 502 | 445 | 8 | 29 | 0 | 20 | 57 | 0 | 57 | 0
236 | Block 5 | 2 | C3 | reviewed | 502 | 455 | 8 | 19 | 0 | 20 | 47 | 0 | 47 | 0
237 | Block 5 | 2 | C3 | submitted | 502 | 450 | 8 | 25 | 0 | 19 | 52 | 0 | 52 | 0
238 | Block 5 | 2 | C3 | submitted | 502 | 448 | 8 | 27 | 0 | 19 | 54 | 0 | 54 | 4
239 | Block 5 | 2 | C3 | submitted | 502 | 461 | 0 | 9 | 0 | 32 | 41 | 0 | 41 | 0
240 | Block 5 | 2 | C3 | submitted | 502 | 465 | 2 | 2 | 0 | 33 | 37 | 0 | 37 | 2
241 | Block 5 | 2 | C3 | submitted | 502 | 468 | 0 | 1 | 0 | 33 | 34 | 0 | 34 | 0
242 | Block 5 | 2 | C3 | paused — RE-INSPECT (data-loss) | 502 | 316 | 154 | 0 | 0 | 32 | 186 | 0 | 186 | 3
243 | Block 5 | 2 | C3 | submitted | 502 | 463 | 0 | 4 | 0 | 35 | 39 | 0 | 39 | 0
041 | Block 6 | 0 | C3 | submitted | 508 | 450 | 8 | 20 | 0 | 30 | 58 | 0 | 58 | 1
042 | Block 6 | 0 | C3 | submitted | 508 | 456 | 8 | 14 | 0 | 30 | 52 | 0 | 52 | 0
043 | Block 6 | 0 | C3 | submitted | 508 | 452 | 8 | 19 | 0 | 29 | 56 | 0 | 56 | 1
044 | Block 6 | 0 | C3 | submitted | 508 | 460 | 8 | 11 | 0 | 29 | 48 | 0 | 48 | 1
045 | Block 6 | 0 | C3 | submitted | 508 | 460 | 8 | 10 | 0 | 30 | 48 | 0 | 48 | 0
046 | Block 6 | 0 | C3 | reviewed | 508 | 456 | 12 | 10 | 0 | 30 | 52 | 0 | 52 | 0
047 | Block 6 | 0 | C3 | reviewed | 508 | 459 | 8 | 11 | 0 | 30 | 49 | 0 | 49 | 0
048 | Block 6 | 0 | C3 | submitted | 508 | 459 | 8 | 11 | 0 | 30 | 49 | 0 | 49 | 1
049 | Block 6 | 0 | C3 | submitted | 508 | 455 | 8 | 15 | 0 | 30 | 53 | 0 | 53 | 0
050 | Block 6 | 0 | C3 | submitted | 508 | 465 | 8 | 6 | 0 | 29 | 43 | 0 | 43 | 0
051 | Block 6 | 0 | C3 | submitted | 508 | 458 | 8 | 12 | 0 | 30 | 50 | 0 | 50 | 0
052 | Block 6 | 0 | C3 | submitted | 508 | 455 | 8 | 16 | 0 | 29 | 53 | 0 | 53 | 0
148 | Block 6 | 1 | C3 | submitted | 502 | 457 | 0 | 15 | 0 | 30 | 45 | 0 | 45 | 0
149 | Block 6 | 1 | C3 | reviewed | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 0
150 | Block 6 | 1 | C3 | reviewed | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 0
151 | Block 6 | 1 | C3 | reviewed | 502 | 451 | 11 | 0 | 0 | 40 | 51 | 0 | 51 | 0
152 | Block 6 | 1 | C3 | reviewed | 502 | 459 | 4 | 0 | 0 | 39 | 43 | 0 | 43 | 0
153 | Block 6 | 1 | C3 | reviewed | 502 | 475 | 4 | 0 | 0 | 23 | 27 | 0 | 27 | 0
154 | Block 6 | 1 | C3 | submitted | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 1
155 | Block 6 | 1 | C3 | submitted | 502 | 459 | 4 | 0 | 0 | 39 | 43 | 0 | 43 | 1
156 | Block 6 | 1 | C3 | reviewed | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 0
157 | Block 6 | 1 | C3 | reviewed | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 0
158 | Block 6 | 1 | C3 | submitted | 502 | 458 | 4 | 0 | 0 | 40 | 44 | 0 | 44 | 1
159 | Block 6 | 1 | C3 | reviewed | 502 | 474 | 4 | 0 | 0 | 24 | 28 | 0 | 28 | 0
252 | Block 6 | 2 | C2 | pending followup | 502 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | Block 6 | 2 | C2 | pending followup | 502 | 372 | 76 | 0 | 0 | 54 | 130 | 4 | 134 | 5
254 | Block 6 | 2 | C2 | pending followup | 502 | 399 | 49 | 0 | 0 | 54 | 103 | 0 | 103 | 3
255 | Block 6 | 2 | C2 | pending followup | 502 | 402 | 46 | 0 | 0 | 54 | 100 | 5 | 105 | 8
256 | Block 6 | 2 | C2 | pending followup | 502 | 401 | 47 | 0 | 0 | 54 | 101 | 1 | 102 | 2
257 | Block 6 | 2 | C3 | reviewed | 502 | 500 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0
258 | Block 6 | 2 | C2 | pending followup | 502 | 374 | 74 | 0 | 0 | 54 | 128 | 7 | 135 | 5
259 | Block 6 | 2 | C2 | pending followup | 502 | 370 | 78 | 0 | 0 | 54 | 132 | 0 | 132 | 29
260 | Block 6 | 2 | C2 | pending followup | 502 | 347 | 101 | 0 | 0 | 54 | 155 | 5 | 160 | 16
261 | Block 6 | 2 | C2 | pending followup | 502 | 349 | 99 | 0 | 0 | 54 | 153 | 2 | 155 | 8
262 | Block 6 | 2 | C2 | pending followup | 502 | 404 | 44 | 0 | 0 | 54 | 98 | 0 | 98 | 9
263 | Block 6 | 2 | C2 | pending followup | 502 | 404 | 44 | 0 | 0 | 54 | 98 | 2 | 100 | 5
053 | Block 7 | 0 | C3 | submitted | 508 | 458 | 8 | 12 | 0 | 30 | 50 | 0 | 50 | 0
054 | Block 7 | 0 | C3 | reviewed | 508 | 453 | 11 | 14 | 0 | 30 | 55 | 0 | 55 | 0
055 | Block 7 | 0 | C3 | submitted | 508 | 459 | 0 | 9 | 0 | 40 | 49 | 0 | 49 | 0
056 | Block 7 | 0 | C3 | submitted | 508 | 461 | 0 | 7 | 0 | 40 | 47 | 0 | 47 | 0
057 | Block 7 | 0 | C3 | submitted | 508 | 450 | 0 | 0 | 0 | 58 | 58 | 0 | 58 | 0
160 | Block 7 | 1 | C2 | pending followup | 502 | 337 | 111 | 0 | 0 | 54 | 165 | 0 | 165 | 7
161 | Block 7 | 1 | C2 | pending followup | 502 | 350 | 98 | 0 | 0 | 54 | 152 | 0 | 152 | 1
162 | Block 7 | 1 | C2 | pending followup | 502 | 359 | 89 | 0 | 0 | 54 | 143 | 0 | 143 | 6
163 | Block 7 | 1 | C3 | reviewed | 502 | 454 | 0 | 11 | 0 | 37 | 48 | 0 | 48 | 0
164 | Block 7 | 1 | C2 | pending followup | 502 | 356 | 92 | 0 | 0 | 54 | 146 | 0 | 146 | 5
165 | Block 7 | 1 | C2 | pending followup | 502 | 344 | 104 | 0 | 0 | 54 | 158 | 0 | 158 | 21
264 | Block 7 | 2 | C2 | submitted | 502 | 382 | 66 | 0 | 0 | 54 | 120 | 0 | 120 | 0
265 | Block 7 | 2 | C2 | submitted | 502 | 372 | 76 | 0 | 0 | 54 | 130 | 0 | 130 | 20
266 | Block 7 | 2 | C2 | pending followup | 502 | 358 | 90 | 0 | 0 | 54 | 144 | 3 | 147 | 14
267 | Block 7 | 2 | C2 | in progress | 502 | 384 | 64 | 0 | 0 | 54 | 118 | 0 | 118 | 1
268 | Block 7 | 2 | C2 | pending followup | 502 | 479 | 0 | 23 | 0 | 0 | 23 | 0 | 23 | 7
269 | Block 7 | 2 | C2 | pending followup | 502 | 499 | 0 | 3 | 0 | 0 | 3 | 0 | 3 | 0
PROJECT TOTAL |  |  |  |  | 95716 | 83046 | 5881 | 2140 | 12 | 4637 | 12670 | 69 | 12739 | 2464